## CS460
Task Name | Start | End | Duration (days)
Kickoff Meeting | 2016-08-26 | 2016-08-27 | 1
Gear VR Prototype Scene Complete | 2016-10-17 | 2016-10-18 | 1
Midterm Presentation | 2016-10-28 | 2016-10-29 | 1
Final Presentation | 2016-12-09 | 2016-12-10 | 1
VR Introduction | 2016-08-29 | 2016-09-02 | 4
Gear VR App Analysis | 2016-09-05 | 2016-11-04 | 60
Gear VR Deployment Testing | 2016-09-26 | 2016-10-14 | 18
Oculus/Unity SDK Configuration | 2016-09-12 | 2016-09-30 | 18
Database Application Development | 2016-10-03 | 2016-11-18 | 46
Presentation Preparation | 2016-10-17 | 2016-10-27 | 10
Design Document Development | 2016-11-07 | 2016-12-29 | 52
Prototype Gear VR Scene (Unity) | 2016-11-21 | 2016-12-07 | 16
Presentation Preparation | 2016-11-28 | 2016-12-07 | 9
| Meetings | 48 hours
Milestone
Research/Analysis
Design/Development
Team Collaboration

## CS465
Task Name | Start | End | Duration (days)
Kickoff Meeting | 2017-01-13 | 2017-01-14 | 1
Finalize Design Document | 2017-01-15 | 2017-01-21 | 6
Implement Scene Management | 2017-01-22 | 2017-01-28 | 6
Implement Main Scene | 2017-01-29 | 2017-02-11 | 13
Implement Menu Structures | 2017-02-12 | 2017-02-18 | 6
Implement Supporting Scenes | 2017-02-19 | 2017-03-10 | 19
Midterm Presentation | 2017-03-17 | 2017-03-18 | 1
Testing | 2017-03-12 | 2017-03-25 | 13
Touch-up and Testing | 2017-03-26 | 2017-04-16 | 21
Poster Design | 2017-04-02 | 2017-04-12 | 10
Testing/Presentation Preparation | 2017-04-17 | 2017-04-28 | 11
Final Presentation | 2017-04-28 | 2017-04-29 | 1
Milestone
Research/Analysis
Design/Development
Team Collaboration

## Hours Breakdown
Phase | S1 | S2 | Hours | Avery | S1 | S2 | Total | Asad | S1 | S2 | Total | Daniel | S1 | S2 | Total
Research | 190 | 64 | 155 |  | 20 | 8 | 28 | Unreported | 20 | 8 | 28 |  | 75 | 24 | 99
Design | 76 | 52 | 128 |  | 18 | 6 | 24 | (Assumed at least Avery's numbers) | 18 | 6 | 24 |  | 40 | 40 | 80
Prototype | 25 | 155 | 180 |  | 0 | 14 | 14 |  | 0 | 14 | 14 |  | 25 | 127 | 152
Total hours : |  |  | 607 |  |  |  | 66 |  |  |  | 66 |  |  |  | 331
[8 empty] | Meeting | S1 | S2 | Total
[9 empty] | 22 | 26 | 48
[8 empty] | Total Man Hours (x3) : |  |  | 144